## WBS
1.0 | 1 | Manajemen Proyek & Persyaratan | Perencanaan, dokumentasi, dan kontrol proyek | Semua | P0 | PRD §1-§10 | Semua lane | Selesai
1.1 | 2 | Manajemen Proyek & Persyaratan | PRD, SRS, arsitektur, desain, BPMN, WBS | Semua | P0 | PRD, SRS, Architect.md, Design.md | - | Selesai
1.2 | 2 | Manajemen Proyek & Persyaratan | Quality gate dan audit kepatuhan `law.bend` | Semua | P0 | L001-L051 | - | Selesai
1.3 | 2 | Manajemen Proyek & Persyaratan | Setup proyek, dependensi, dan konfigurasi environment | Admin | P0 | NFR-05, NFR-09 | - | Selesai
2.0 | 1 | Fondasi Aplikasi | Fondasi teknis aplikasi | Sistem | P0 | Architect.md §3-§7 | Sistem | Selesai
2.1 | 2 | Fondasi Aplikasi | Django project, settings, SQLite/PostgreSQL, media | Sistem | P0 | NFR-05 | - | Selesai
2.2 | 2 | Fondasi Aplikasi | Model, constraint, index, dan migration | Sistem | P0 | Architect.md ERD, L030 | - | Selesai
2.3 | 2 | Fondasi Aplikasi | Login, logout, role-based access | Semua | P0 | F-01, FR-001-FR-003 | Semua lane | Selesai
2.4 | 2 | Fondasi Aplikasi | State machine terpusat + AuditLog atomik | Sistem | P0 | F-12, FR-060, L020, L022 | Sistem: validasi & audit | Selesai
2.5 | 2 | Fondasi Aplikasi | Penomoran otomatis PR/RFQ/PO/GR | Sistem | P0 | FR-020, FR-030, FR-040 | - | Selesai
2.6 | 2 | Fondasi Aplikasi | Seed data, akun demo, dan data contoh | Admin | P0 | NFR-09 | Admin | Selesai
3.0 | 1 | Master Data | Pengelolaan data referensi | Admin | P0 | F-02 | Admin | Selesai
3.1 | 2 | Master Data | CRUD department | Admin | P0 | FR-010 | Admin: master data | Selesai
3.2 | 2 | Master Data | CRUD item (kode unik, nama, satuan) | Admin | P0 | FR-010 | Admin: master data | Selesai
3.3 | 2 | Master Data | CRUD vendor (kode unik, kontak, email, telepon) | Admin | P0 | FR-010 | Admin: master data | Selesai
3.4 | 2 | Master Data | Pengelolaan user dan role | Admin | P0 | F-01, F-02 | Admin: master data | Selesai
3.5 | 2 | Master Data | Nonaktifkan data terpakai (`is_active=False`) | Admin | P0 | FR-011 | - | Selesai
4.0 | 1 | Purchase Request & Approval | Siklus PR dari draft sampai siap sourcing | Requester, Dept Head, Officer | P0 | F-03, F-04, F-05 | Requester, Dept Head, Officer | Selesai
4.1 | 2 | Purchase Request & Approval | Buat PR multi-item (item, qty > 0, catatan) | Requester | P0 | FR-020 | Requester: buat PR | Selesai
4.2 | 2 | Purchase Request & Approval | Edit/hapus PR selama `DRAFT` | Requester | P0 | FR-021 | Requester: revisi | Selesai
4.3 | 2 | Purchase Request & Approval | Submit PR + buat approval Dept Head | Requester, Sistem | P0 | FR-022 | Requester: submit | Selesai
4.4 | 2 | Purchase Request & Approval | Approve PR oleh Dept Head | Dept Head | P0 | FR-023, BR-01 | Dept Head: approve | Selesai
4.5 | 2 | Purchase Request & Approval | Reject PR + alasan dan revisi ke `DRAFT` | Dept Head, Requester | P0 | FR-023, FR-024 | Dept Head: reject; Requester: revisi | Selesai
4.6 | 2 | Purchase Request & Approval | Batalkan PR sesuai role dan state machine | Requester/Officer/Manager/Admin | P1 | BR-06, state machine | Requester: batalkan | Selesai
4.7 | 2 | Purchase Request & Approval | Pembatasan akses PR per role dan departemen | Semua | P0 | FR-003, FR-023 | Semua lane | Selesai
4.8 | 2 | Purchase Request & Approval | Daftar PR: filter, pencarian, pagination, detail | Semua | P1 | F-13, F-15, FR-061-FR-062 | Sistem: dashboard | Selesai
5.0 | 1 | Sourcing | RFQ, quotation, perbandingan, dan pemilihan vendor | Officer, Manager, Vendor | P0 | F-06, F-07, F-08, F-09 | Officer, Vendor, Manager | Selesai
5.1 | 2 | Sourcing | Buat RFQ dari PR `APPROVED`, pilih >= 1 vendor | Officer | P0 | FR-025, FR-030 | Officer: buat RFQ | Selesai
5.2 | 2 | Sourcing | Kirim/tutup RFQ (`SENT`, `CLOSED`) | Officer | P0 | FR-031 | Officer: kirim RFQ | Selesai
5.3 | 2 | Sourcing | Input quotation per vendor dan per item | Officer | P0 | FR-032 | Officer: input quotation | Selesai
5.4 | 2 | Sourcing | Lampiran file penawaran (PDF/gambar) | Officer | P1 | FR-032 | Officer: input quotation | Selesai
5.5 | 2 | Sourcing | AI extractor penawaran (opsional) sebagai prefill form | Officer | P2 | F-16, FR-070-FR-072 | Officer: input quotation | Selesai
5.6 | 2 | Sourcing | Tabel perbandingan harga per item dan total vendor | Officer, Manager | P0 | FR-033 | Officer: bandingkan | Selesai
5.7 | 2 | Sourcing | Pilih vendor + justifikasi jika bukan harga terendah | Officer | P0 | FR-034, BR-02 | Officer: pilih vendor | Selesai
5.8 | 2 | Sourcing | Revisi quotation setelah ditolak Manager | Officer | P0 | F-09, state machine | Officer: revisi quotation | Selesai
5.9 | 2 | Sourcing | Approval/reject vendor terpilih oleh Manager | Manager | P0 | FR-035, BR-01 | Manager: approval vendor | Selesai
6.0 | 1 | Purchase Order | Penerbitan, approval, pengiriman, dan cetak PO | Officer, Manager | P0 | F-09, F-10, F-14 | Officer, Manager | Selesai
6.1 | 2 | Purchase Order | Terbitkan PO dari quotation `APPROVED` dan RFQ `AWARDED` | Officer | P0 | FR-040, BR-03 | Officer: terbitkan PO | Selesai
6.2 | 2 | Purchase Order | Approval/reject PO oleh Manager | Manager | P0 | FR-041, FR-043 | Manager: approval PO | Selesai
6.3 | 2 | Purchase Order | Tandai PO terkirim ke vendor | Officer | P0 | FR-042 | Officer: kirim PO | Selesai
6.4 | 2 | Purchase Order | Cetak/print view PO | Officer | P1 | F-14, FR-042 | Officer: kirim PO | Selesai
6.5 | 2 | Purchase Order | Revisi/ajukan ulang atau batalkan PO | Officer, Manager | P1 | FR-043, BR-06 | Officer: revisi/batalkan PO | Selesai
6.6 | 2 | Purchase Order | Daftar/detail PO: filter, pencarian, pagination | Semua | P1 | F-15, FR-062 | Sistem: dashboard | Selesai
7.0 | 1 | Goods Receipt | Pencatatan penerimaan barang/jasa | Warehouse | P0 | F-11 | Warehouse | Selesai
7.1 | 2 | Goods Receipt | Buat GR untuk PO `SENT`/`PARTIALLY_RECEIVED` | Warehouse | P0 | FR-050 | Warehouse: buat GR | Selesai
7.2 | 2 | Goods Receipt | Dukungan penerimaan sebagian (partial receipt) | Warehouse | P0 | FR-052 | Warehouse: partial receipt | Selesai
7.3 | 2 | Goods Receipt | Validasi qty tidak melebihi sisa PO | Warehouse, Sistem | P0 | FR-051, BR-05 | Warehouse: validasi qty | Selesai
7.4 | 2 | Goods Receipt | Kondisi barang (OK/RUSAK) dan catatan | Warehouse | P0 | FR-050 | Warehouse: buat GR | Selesai
7.5 | 2 | Goods Receipt | Update status PO/PR menjadi `PARTIALLY_RECEIVED`/`COMPLETED` | Sistem | P0 | FR-052 | Warehouse: selesai | Selesai
7.6 | 2 | Goods Receipt | Daftar/detail GR | Warehouse | P1 | F-15 | Warehouse | Selesai
8.0 | 1 | Lintas Fungsi | Dashboard, UX, audit, dan pencarian | Semua | P1 | F-12, F-13, F-15 | Sistem | Selesai
8.1 | 2 | Lintas Fungsi | Dashboard ringkasan status dan antrean per role | Semua | P1 | FR-061 | Sistem: dashboard | Selesai
8.2 | 2 | Lintas Fungsi | Filter status, pencarian nomor, pagination 20/halaman | Semua | P1 | FR-062 | Sistem: dashboard | Selesai
8.3 | 2 | Lintas Fungsi | UI Bootstrap 5 + HTMX, responsif, badge status | Semua | P1 | Design.md | Semua lane | Selesai
8.4 | 2 | Lintas Fungsi | Tampilan riwayat audit pada detail dokumen | Semua | P0 | F-12, FR-060 | Sistem: audit | Selesai
8.5 | 2 | Lintas Fungsi | Pesan error domain dan feedback aksi | Semua | P1 | NFR-08 | Semua lane | Selesai
8.6 | 2 | Lintas Fungsi | Upload dan penyajian file media | Officer | P1 | FR-032 | Officer: input quotation | Selesai
9.0 | 1 | QA, Gate, dan Delivery | Pengujian, kepatuhan, dan dokumentasi | Semua | P0 | NFR-06-NFR-09 | - | Selesai
9.1 | 2 | QA, Gate, dan Delivery | Unit/service test aturan bisnis dan state machine | Semua | P0 | NFR-07, L033 | - | Selesai
9.2 | 2 | QA, Gate, dan Delivery | Integration test happy path, reject, partial receipt | Semua | P0 | PRD §9 | - | Selesai
9.3 | 2 | QA, Gate, dan Delivery | View/template smoke test dan regresi bug | Semua | P0 | NFR-07 | - | Selesai
9.4 | 2 | QA, Gate, dan Delivery | Menjalankan seluruh gate `law.bend` | Semua | P0 | L001-L051 | - | Selesai
9.5 | 2 | QA, Gate, dan Delivery | `ruff check`, `ruff format --check` | Semua | P1 | L035 | - | Selesai
9.6 | 2 | QA, Gate, dan Delivery | Cek migrasi dan `manage.py check` | Semua | P0 | L030 | - | Selesai
9.7 | 2 | QA, Gate, dan Delivery | README, seed demo, dan panduan menjalankan | Semua | P0 | NFR-09 | - | Selesai

## Ringkasan
Modul | Jumlah Fitur | Fitur Utama
Manajemen Proyek & Persyaratan | 3 | Dokumen, arsitektur, quality gate
Fondasi Aplikasi | 6 | Auth/RBAC, state machine, audit, numbering
Master Data | 5 | Department, item, vendor, user
Purchase Request & Approval | 8 | PR, submit, approve/reject, revisi, cancel
Sourcing | 9 | RFQ, quotation, AI, comparison, selection
Purchase Order | 6 | PO, approval, send, print, cancel
Goods Receipt | 6 | GR, partial, over-receipt guard, completion
Lintas Fungsi | 6 | Dashboard, search, UI, audit, media
QA, Gate, dan Delivery | 7 | Test, lint, migration, law gates, docs

## Info
Dokumen | WBS Aplikasi Procurement
Versi | 1.0
Sumber | docs/WBS.md
Rujukan | PRD.md, SRS.md, docs/BPMN.md
Keterangan | WBS ini memetakan modul, fitur, role, prioritas, FR, dan task BPMN.
Status | Selaras dengan implementasi pada commit terakhir.